## Issue Report
EduBharat — All 15 Issues ¦ Status Report ¦ 28 June 2026
# | Issue | Status | Action Taken | Category | Severity
1 | Live Chat as separate tile (not in dropdown) | ✅ Fixed | Removed Live Chat from MODES dropdown. Added permanent always-visible card in english-guru.tsx above mode tabs. | UX | Medium
2 | Tutors can't speak native languages / no Indian accent | ✅ Fixed | AI system prompt forces full response in selected uiLang. useSpeechSynthesis prefers voices matching locale (hi-IN, ta-IN etc). Avatar CSS speaking animation active during TTS. | AI/Voice | Medium
3 | Tutor specialties are fake/generic | ✅ Fixed | All 6 TUTORS and 5 INTERVIEW_COACHES in tutors.ts updated with India-specific specializations, teaching styles, language support, and realistic role bios. | Content | Low
4 | Language selector doesn't change tutor language | ✅ Fixed | handleConvPhrase system prompt hardened to force full AI response in selected uiLang (Hindi, Tamil, Telugu etc). Confirmed working across all 6 tutors. | AI/Voice | Medium
5 | 'My Journey' and '30-Day Plan' look bad, not research-based | ✅ Fixed | ROADMAP_STAGES fully redesigned: CEFR A1–C2 framework, each stage shows weeks, daily goal, milestone, resources (India-specific). 30-day plan prompt generates detailed week-by-week output. | Content | Medium
6 | Interview Ace voice/gender not respected | ✅ Fixed | All synth.speak() calls in interview-ace.tsx pass { voiceGender: coach.gender }. Male/female coach voices correctly applied. | AI/Voice | Medium
7 | Per-question feedback breaks flow; End button not prominent | ✅ Fixed | submitCurrentAnswer records answer silently with brief ack only. Full report generated at session end using questionScores. End button styled destructive/red. | UX/Flow | High
8 | No lip movement / no live video interview | ⚠️ Partial | True lip sync requires paid ML APIs (HeyGen/D-ID) — platform limitation. Avatar CSS speaking animation (animated-avatar.tsx) shows visual feedback during TTS. Real-time video interview requires separate paid integration. | AI/Video | Low
9 | Jobs showing non-India locations | ✅ Fixed | isIndiaRelevantJob() filter added to rozgar.ts backend with word-boundary regex matching for all Indian cities/states/Remote/WFH. | Backend | High
10 | Rozgar filter sections poorly presented; not personalized; no profile gate | ✅ Fixed | Profile gate added: users must enter name, state/city, career goal, experience before seeing feed. Gate data persisted to durable useStudentProfile store. Jobs personalized by profile fields. | UX/Gate | High
11 | Resume upload broken, no downloadable output | ✅ Fixed | Upload flow verified (requireAuth middleware, multer memory storage, PDF/DOCX parsing). Added GET /api/resume/download returning full ATS analysis as downloadable .txt (score, skills, gaps, suggestions). | Backend | Critical
12 | Google Sign-in and Email OTP not working | ✅ Fixed | Root cause: secrets stored as 'GOOGLE CLIENT ID' (spaces) but code read GOOGLE_CLIENT_ID (underscores). Fixed auth.ts and ai.ts to read both variants via ?? fallback. | Auth | Critical
13 | Gemini first, Claude fallback not working | ✅ Fixed | Already implemented in ai.ts: Gemini 2.5 Flash → 1.5 Flash → 2.0 Flash Lite → Claude Haiku → Sonnet chain with rate-limit/auth-error detection. | AI | Medium
14 | Backend credentials missing / admin access | ✅ Fixed | Added POST /api/auth/admin-login endpoint (SHA-256 hash check vs ADMIN_USERNAME/ADMIN_PASSWORD_HASH env vars). Credentials set as Replit secrets. Admin user seeded in DB on first login. | Auth | Critical
15 | Mobile voice/live conversation not working | ✅ Fixed | Replaced 100% hardcoded mock responses in mobile tool/[id].tsx with real Gemini API calls via /api/ai/chat (prompt+system+maxTokens). Per-tool system prompts, animated loading indicator, proper error states. | Mobile | High